## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1
3641065 | 68221 | ATM Project | 9 | ATM_1-9 | 292192 | Bug | 92387 | Withdraw | 63746 | 1.0 | Withdraw amounts are offset | found in both exploratory testing and MFT: When a withdraw is performed, you receive the wrong amount (offset) How to reproduce: 1. Launch ATM System 2. turn on, using system power button 3. Insert card with the "Click to insert card" button 4. access card "1" with PIN: "42" 5. Choose option "1) Withdrawal" 6. Choose "2) Savings" 7. Select an option listed Expected Results: Output money matches option chosen Actual: withdraw $20.00 gives 40.00 withdraw $40.00 gives 60.00 withdraw $60.00 gives 100.00 withdraw $100.00 gives 200.00 withdraw $200.00 gives 20.00 Tested version 1.0 on 64-bit Windows 10 openjdk 17.0.1 2021-10-19 OpenJDK Runtime Environment (build 17.0.1+12-39) OpenJDK 64-Bit Server VM (build 17.0.1+12-39, mixed mode, sharing) ![image][screen_040.png] Option 4) $100.00 gave $200.00 | 3 | Resolved | 2 | High | 63749 | 1.1 |  |  | 319513 | LAB1-27 | 319513 | LAB1-27 | Jan. 22, 2022 17:12 |  | 319513 | LAB1-27 | Jan. 23, 2022 15:01 | 1 | 0
3641442 | 68221 | ATM Project | 11 | ATM_1-11 | 292192 | Bug | 92391 | Card and PIN validation | 63749,63746 | 1.1,1.0 | Re-enter pin twice after doing it incorrectly | Found in both exploratory testing and MFT. After entering the pin incorrectly any time (1 or 2 times), the correct pin needs to be entered twice in order for the ATM transaction menu to appear. ![image][pasted-2022.01.23-14.51.32.png] How to reproduce: 1. Launch ATM simulation 2. Turn on ATM 3. Insert card with the "Click to insert card" button 4. Enter "1" for card number 5. Enter incorrect pin (anything not "42") 6. Enter correct pin Expected Results: Transaction menu appears Actual: Normal pin entry window appears Tested version 1.0 on 64-bit Windows 10 openjdk 17.0.1 2021-10-19 OpenJDK Runtime Environment (build 17.0.1+12-39) OpenJDK 64-Bit Server VM (build 17.0.1+12-39, mixed mode, sharing) | 2 | In Progress | 3 | Normal | 63749 | 1.1 |  |  | 319513 | LAB1-27 | 319513 | LAB1-27 | Jan. 23, 2022 14:52 |  | 319513 | LAB1-27 | Jan. 23, 2022 14:59 | 1 | 0 | Jan. 23, 2022 14:53 LAB1-27 Defect still exists in version 1.1
3641443 | 68221 | ATM Project | 12 | ATM_1-12 | 292192 | Bug | 92392 | Deposit | 63749 | 1.1 | Deposit Amount Deducted by $0.10 | found in regression testing: When a deposit is performed, $0.10 are removed from the deposit amount. How to reproduce: 1. Launch ATM System 2. turn on, using system power button 3. Insert card with the "Click to insert card" button 4. access card "1" with PIN: "42" 5. Choose option "2) Deposit" 6. Choose "1) Checking" 7. Enter an amount such as "$5.00" and press "Enter" 8. "Click to insert Envelope" 9. System adds "$5.00" but removes $0.10 Expected Results: NO $0.10 Deduction Actual: $0.10 Deduction from account Tested version 1.0 on 64-bit Windows 10 openjdk 17.0.1 2021-10-19 OpenJDK Runtime Environment (build 17.0.1+12-39) OpenJDK 64-Bit Server VM (build 17.0.1+12-39, mixed mode, sharing) ![image][pasted-2022.01.23-14.55.44.png] | 2 | In Progress | 2 | High | 63750 | 1.2 |  |  | 319513 | LAB1-27 | 319513 | LAB1-27 | Jan. 23, 2022 14:56 |  | 319513 | LAB1-27 | Jan. 23, 2022 14:58 | 1 | 0 | Jan. 23, 2022 14:58 LAB1-27 When testing if issue "ATM_1-6 Deposit Amount Deducted by $10" was fixed through regression testing, the issue resulted in this issue being created.
3641054 | 68221 | ATM Project | 6 | ATM_1-6 | 292192 | Bug | 92392 | Deposit | 63746 | 1.0 | Deposit Amount Deducted by $10 | found in both exploratory testing and MFT: When a deposit is performed, $10.00 are removed from the deposit amount. How to reproduce: 1. Launch ATM System 2. turn on, using system power button 3. Insert card with the "Click to insert card" button 4. access card "1" with PIN: "42" 5. Choose option "2) Deposit" 6. Choose "1) Checking" 7. Enter an amount such as "$5.00" and press "Enter" 8. "Click to insert Envelope" 9. System adds "$5.00" but removes $10.00 Expected Results: NO $10.00 Deduction Actual: $10.00 Deduction from account Tested version 1.0 on 64-bit Windows 10 openjdk 17.0.1 2021-10-19 OpenJDK Runtime Environment (build 17.0.1+12-39) OpenJDK 64-Bit Server VM (build 17.0.1+12-39, mixed mode, sharing) ![image][pasted-2022.01.22-16.41.36.png] ![image][pasted-2022.01.22-16.42.14.png] | 3 | Resolved | 2 | High | 63749 | 1.1 |  |  | 319513 | LAB1-27 | 319513 | LAB1-27 | Jan. 22, 2022 16:43 |  | 319513 | LAB1-27 | Jan. 23, 2022 14:51 | 1 | 0
3641048 | 68221 | ATM Project | 5 | ATM_1-5 | 292192 | Bug | 92393 | Money Transfer | 63746 | 1.0 | Transfer amount is $0.50 less | Found both in Exploratory and MFT When transferring between accounts, the amount sent is $0.50 less than expected. How to reproduce: 1. Launch ATM system 2. Turn on system 3. Enter any number of $20 bills 4. Insert card 5. Enter card ID 6. Press 3 on the transaction menu 7. Pick two different accounts (ex. transfer from Checking to Savings) 8. Enter an amount (ex. $10.00) Expected results: AMOUNT: $10.00 Actual results: AMOUNT $9.50 Tested version 1.0 on 64-bit Windows 10 openjdk 17.0.1 2021-10-19 OpenJDK Runtime Environment (build 17.0.1+12-39) OpenJDK 64-Bit Server VM (build 17.0.1+12-39, mixed mode, sharing) ![image][pasted-2022.01.22-16.33.00.png] | 3 | Resolved | 2 | High | 63749 | 1.1 |  |  | 319513 | LAB1-27 | 319513 | LAB1-27 | Jan. 22, 2022 16:34 |  | 319513 | LAB1-27 | Jan. 23, 2022 14:51 | 1 | 0
3640972 | 68221 | ATM Project | 2 | ATM_1-2 | 292192 | Bug | 92387,92392,92393,92395,92396 | Withdraw,Deposit,Money Transfer,Transaction Cacellation,Balance Inquiry | 63746 | 1.0 | Application freezes out | After entering the card number and pin, if you click any invalid option, the application will not allow any action while an increasingly larger "$20.00" appears below the screen. No buttons are functional during this time. This occurs anywhere from 1 to 10 times with no error message appearing. How to reproduce: 1. Launch ATM System 2. turn on, using system power button 3. Insert card with the "Click to insert card" button 4. Enter card ID and pin 5. Press 0, 5, 6, 7, 8 or 9 Expected Results: Nothing happens or an error message appears Actual Results: $20.00 shows up and error sounds play. Window prevents further actions for a small period of time. Tested version 1.0 on 64-bit Windows 10 openjdk 17.0.1 2021-10-19 OpenJDK Runtime Environment (build 17.0.1+12-39) OpenJDK 64-Bit Server VM (build 17.0.1+12-39, mixed mode, sharing) ![image][Screenshot_1.jpg] | 3 | Resolved | 2 | High | 63749 | 1.1 |  |  | 319513 | LAB1-27 | 319513 | LAB1-27 | Jan. 22, 2022 14:39 |  | 319513 | LAB1-27 | Jan. 23, 2022 14:10 | 1 | 0
3641057 | 68221 | ATM Project | 7 | ATM_1-7 | 292192 | Bug | 92396 | Balance Inquiry | 63746 | 1.0 | Balance Inquiry of Option 2 Unknown Error | When User requests a balance inquiry on Option 2) an Unknown Error shows on the screen, the $500 dollar animation appears. Initial state of the system: System is asking which account to get a balance inquiry from How to reproduce: 1. Insert any number of $20 bills 2. Log into Card Number 1 3. Press 4 for Balance inquiry 4. Press 2 Expected: No error and animation Total Balance shows $1000 for Savings and $5000 for Money Market Actual: Unknown Error shows on the screen. $500 dollar animation shows up 1.0 shows Total Balance shows $1000 for Money Market even though Money Market is stated to have $5000 | 2 | In Progress | 3 | Normal | 63750 | 1.2 |  |  | 319513 | LAB1-27 | 319513 | LAB1-27 | Jan. 22, 2022 16:45 |  | 319513 | LAB1-27 | Jan. 23, 2022 14:07 | 0 | 0 | Jan. 23, 2022 14:07 LAB1-27 Defect still exists in version 1.1.
3641020 | 68221 | ATM Project | 4 | ATM_1-4 | 292192 | Bug | 92391 | Card and PIN validation | 63746 | 1.0 | Leading Zeros Ignored | During Card and PIN validation the leading zeros entered are ignored. How to reproduce: 1. Launch ATM System 2. turn on, using system power button 3. Insert card with the "Click to insert card" button 4. card ID: "1" also accepts "0001" or any input that end in 1 regardless of the number of leading zeros 5. the same applys to the PIN, so for example the PIN "42" also accepts "0042" Expected Results: Card Ejection with error message "FAILURE invalid card" or "PIN was incorrect" Actual: Card is accepted and System gives access to menu screen Tested version 1.0 on 64-bit Windows 10 openjdk 17.0.1 2021-10-19 OpenJDK Runtime Environment (build 17.0.1+12-39) OpenJDK 64-Bit Server VM (build 17.0.1+12-39, mixed mode, sharing) | 2 | In Progress | 3 | Normal | 63750 | 1.2 |  |  | 319513 | LAB1-27 | 319513 | LAB1-27 | Jan. 22, 2022 16:20 |  | 319513 | LAB1-27 | Jan. 23, 2022 14:06 | 0 | 0 | Jan. 23, 2022 14:06 LAB1-27 Defect still exists in version 1.1.
3641005 | 68221 | ATM Project | 3 | ATM_1-3 | 292192 | Bug | 92387 | Withdraw | 63746 | 1.0 | Withdrawal $200 from $100 checking account withdrawals $20 dollars | When Customer attempts to withdraw $200 from $100 checking account, $20 is withdrawn from their account. How to reproduce: 1. Turn on ATM system 2. Insert at least 10 $20 dollar bills 2. Log into Card number 1 account 3. Choose option 1 to withdraw 4. Choose Option 1 to withdraw from checking account 5. Choose option 5 to withdraw $200 Expected Results: Insufficient available Balance Actual: $20 is withdrawn from their account. | 3 | Resolved | 3 | Normal | 63749 | 1.1 |  |  | 319513 | LAB1-27 | 319513 | LAB1-27 | Jan. 22, 2022 16:12 |  | 319513 | LAB1-27 | Jan. 23, 2022 13:20 | 0 | 0
3641066 | 68221 | ATM Project | 10 | ATM_1-10 | 292192 | Bug | 92387,92392,92393,92395,92396 | Withdraw,Deposit,Money Transfer,Transaction Cacellation,Balance Inquiry | 63746 | 1.0 | "Wood" vs "Would" | Spelling mistake. How to reproduce: 1. Launch ATM System 2. turn on, using system power button 3. Insert card with the "Click to insert card" button 4. access card "1" with PIN: "42" 5. Choose option "2) Deposit" 6. Choose "1) Checking" 7. Enter an amount such as "$20.00" and press "Enter" 8. "Click to insert Envelope" Expected Results: System prompts "Would you like to do another transaction?" Actual: System prompts "Wood you like to do another transaction?" Tested version 1.0 on 64-bit Windows 10 openjdk 17.0.1 2021-10-19 OpenJDK Runtime Environment (build 17.0.1+12-39) OpenJDK 64-Bit Server VM (build 17.0.1+12-39, mixed mode, sharing) ![image][pasted-2022.01.22-16.41.36.png] ![image][screen_041.png] | 3 | Resolved | 4 | Low | 63749 | 1.1 |  |  | 319513 | LAB1-27 | 319513 | LAB1-27 | Jan. 22, 2022 17:24 |  | 319513 | LAB1-27 | Jan. 23, 2022 12:54 | 1 | 0
3641060 | 68221 | ATM Project | 8 | ATM_1-8 | 292192 | Bug | 92396 | Balance Inquiry | 63746 | 1.0 | "Savings" option under "Balance Inquiry" not showing | When a user selects "Balance Inquiry" from the transaction type menu, "Savings" is not an available menu option. How to reproduce: 1. Launch ATM system 2. Turn on, using system power button 3. Insert card with the "Click to Insert card" button 4. Enter card ID "1", then press "RETURN" 5. Enter pin "42", then press "ENTER" 6. Enter "4" to select "Balance Inquiry" Expected Results: A "Savings" menu option should be displayed. Actual: Only "Checking" and "Money Market" menu options are displayed. ![image][Screenshot 2022-01-22 at 4.41.51 PM.png] Tested version 1.0 on macOS Monterey Version 12.1 openjdk version "11.0.9.1" 2020-11-04 OpenJDK Runtime Environment AdoptOpenJDK (build 11.0.9.1+1) OpenJDK 64-Bit Server VM AdoptOpenJDK (build 11.0.9.1+1, mixed mode) | 3 | Resolved | 2 | High | 63749 | 1.1 |  |  | 319513 | LAB1-27 | 319513 | LAB1-27 | Jan. 22, 2022 16:52 |  | 319513 | LAB1-27 | Jan. 23, 2022 12:53 | 1 | 0